## ID Tasks Overview
Task # | Task Description | # Days | Start Date | End Date | % Complete
2.0 | LearnCanada - Instructional Design | 2410 | Fri 9/15/00 | Mon 2/25/02 | 0%
2.1 | Phase 1 - Orientation and Team Formation | 520 | Fri 9/15/00 | Fri 12/8/00 | 0%
2.1.1 | I.D. Component Design | 5 | Fri 9/15/00 | Thu 9/21/00 | 100%
2.1.2 | Verification of Focus, Tasks and Timelines | 11 | Fri 9/22/00 | Wed11/1/00 | 100%
2.1.3 | Creation of Records and Resources | 12 | Mon 9/25/00 | Wed1/31/02 | 30%
2.1.4 | Event planning | 160 | Mon 9/15/00 | Wed1/31/02 | 10%
2.1.5 | Teacher coordination | 139 | Mon 9/15/00 | Wed1/31/02 | 10%
2.1.6 | Monthly Meetings | 21 | Mon 11/1/00 | Fri 3/30/02 | 12%
2.1.6.1 | 2000-11-01 | 1 | Mon 11/1/00 | Mon 11/1/00 | 100%
2.1.6.2 | 2000-11-15 | 1 | 2000-11-15 | 2000-11-15 | 100%
2.1.6.3 | 2000-12-01 | 1 | 2000-12-01 | 2000-12-01 | 100%
2.1.6.4 | 2000-12-15 | 1 | 2000-12-15 | 2000-12-15 | 0%
2.1.6.5 | 2001-01-15 | 1 | 2001-01-15 | 2001-01-15 | 0%
2.1.6.6 | 2001-02-02 | 1 | 2001-02-02 | 2001-02-02 | 0%
2.1.6.7 | 2001-02-16 | 1 | 2001-02-16 | 2001-02-16 | 0%
2.1.6.8 | 2001-03-02 | 1 | 2001-03-02 | 2001-03-02 | 0%
2.1.6.9 | 2001-04-06 | 1 | 2001-04-06 | 2001-04-06 | 0%
2.1.6.10 | Meetings as needed (1/month) | 12 | 2001-05-01 | 2002-03-30 | 0%
2.1.7 | Organization of Project Development | 66 | Mon 10/9/00 | Fri 1/30/01 | 80%
2.1.8 | Collection of Resources | 36 | Mon 11/6/00 | 2001-03-30 | 30%
2.1.9 | Identification of Project-based learning Projects | 40 | Mon 12/4/00 | Fri 1/30/01 | 50%
2.1.10 | Ottawa Retreat | 30 | Thu 10/12/00 | Fri 10/13/00 | 100%
2.2 | Phase 2 - Requirement Definition and Development | 1286 | Fri 9/15/00 | Thu 9/13/01 | 0%
2.2.1 | Definition of Software Requirements | 6 | Fri 9/15/00 | 2001-01-30 | 0%
2.2.2 | Assessment of Exisiting Content | 6 | Fri 9/22/00 | 2001-02-15 | 0%
2.2.3 | Develop PBL Projects | 672 | 2000-09-15 | 2002-10-15 | 10%
2.2.4 | Conferences and Reports Sept 2000-June 2001 | 368 | Mon 10/30/00 | Mon 4/23/01 | 0%
2.2.4.1 | On-line Conference #1 | 30 | Mon 10/30/00 | Mon 10/30/00 | 100%
2.2.4.2 | Small Group On-line | 1 | Thu 11/16/00 | Thu 11/16/00 | 100%
2.2.4.3 | Small Group On-line | 1 | Thu 12/7/00 | Thu 12/7/00 | 0%
2.2.4.4 | On-line Conference #2 | 30 | Thu 11/30/00 | Thu 11/30/00 | 100%
2.2.4.5 | Lead Report #1 Due | 1 | Fri 12/1/00 | Fri 12/1/00 | 100%
2.2.4.6 | On-line Conference #3 | 30 | Thu 12/14/00 | Thu 12/14/00 | 0%
2.2.4.7 | Lead Report #2 Due | 1 | Fri 12/22/00 | Fri 12/22/00 | 0%
2.2.4.8 | Small Group on-line | 1 | Thu 1/18/01 | Thu 1/18/01 | 0%
2.2.4.9 | Small Group on-line | 1 | Thu 1/25/01 | Thu 1/25/01 | 0%
2.2.4.10 | Lead Report #3 due | 1 | Wed 1/31/01 | Wed 1/31/01 | 0%
2.2.4.11 | On-line Conference #4 | 30 | Thu 2/8/01 | Thu 2/8/01 | 0%
2.2.4.12 | Small Group on-line | 1 | Thu 2/15/01 | Thu 2/15/01 | 0%
2.2.4.13 | Lead Report #4 Due | 1 | Wed 2/28/01 | Wed 2/28/01 | 0%
2.2.4.14 | On-line Conference #5 | 30 | Thu 3/1/01 | Thu 3/1/01 | 0%
2.2.4.15 | Small Group on-line | 1 | Thu 3/15/01 | Thu 3/15/01 | 0%
2.2.4.16 | Lead Report #5 Due | 1 | Fri 3/30/01 | Fri 3/30/01 | 0%
2.2.4.17 | On-line Conference #6 | 30 | Thu 4/5/01 | Thu 4/5/01 | 0%
2.2.4.18 | Small Group on-line | 1 | Thu 4/19/01 | Thu 4/19/01 | 0%
2.2.4.19 | Lead Report #7 due | 30 | Fri 4/20/01 | Fri 4/20/01 | 0%
2.2.4.20 | Conferences and Reports Sept 2001-Jan 2002 | 146 | Mon 4/23/01 | Mon 4/23/01 | 0%
2.2.5 | Program Evaluation | 42 | Wed 11/1/00 | Thu 9/13/01 | 0%
2.2.6 | CA*Net Conference:Inf / MM Focus Group | 36 | 2001-02-01 | 2001-02-01 | 0%
2.2.7 | Evaluation/Modification of PBL Projects | 156 | 2001-03-01 | 2001-03-01 | 0%
2.3 | Phase 3 - Deployment and Evaluation | 476 | Thu 9/13/01 | Fri 12/28/01 | 0%
2.3.1 | Modification of Objects | 132 | Thu 9/13/01 | Thu 10/11/01 | 0%
2.3.2 | Implementation of Projects | 190 | Thu 10/11/01 | Thu 11/22/01 | 0%
2.3.3 | Presentations- PD Day | 12 | Thu 11/22/01 | Fri 11/23/01 | 0%
2.3.4 | Presentations to Other Groups | 26 | Fri 11/23/01 | Fri 12/7/01 | 0%
2.3.5 | CA*Net Conference/Outreach Efforts/Feedback | 40 | Fri 12/7/01 | Fri 12/14/01 | 0%
2.3.6 | CA*Net Conference Evaluation of Infrastructure/Software | 40 | Fri 12/14/01 | Fri 12/21/01 | 0%
2.3.7 | Testing of Final Products | 36 | Fri 12/21/01 | Fri 12/28/01 | 0%
2.4 | Phase 4 - Promotion/ Expansion Acitivities and Management | 128 | Mon 10/1/01 | Wed 2/20/02 | 0%
2.4.1 | National Conference | 42 | Mon 10/1/01 | Fri 10/5/01 | 0%
2.4.2 | International Conference | 42 | Thu 2/14/02 | Wed 2/20/02 | 0%
2.4.2.1 | International Conference Report Preparation | 0 | Thu 2/14/02 | Wed 2/20/02 | 0%
2.4.2.2 | Conference delivery of Report | 0 | Wed 2/20/02 | Wed 2/20/02 | 0%
2.5 | Project Management | 44 | Mon 9/18/00 | Mon 2/25/02 | 0%
2.5.1 | Project Management | 1 | Mon 9/18/00 | Mon 9/18/00 | 0%
2.5.2 | Project Management | 1 | Mon 10/9/00 | Mon 10/9/00 | 0%
2.5.3 | Project Management | 1 | Mon 10/30/00 | Mon 10/30/00 | 0%
2.5.4 | Project Management | 1 | Mon 11/20/00 | Mon 11/20/00 | 0%
2.5.5 | Project Management | 1 | Mon 12/11/00 | Mon 12/11/00 | 0%
2.5.6 | Project Management | 1 | Mon 1/1/01 | Mon 1/1/01 | 0%
2.5.7 | Project Management | 1 | Mon 1/22/01 | Mon 1/22/01 | 0%
2.5.8 | Project Management | 1 | Mon 2/12/01 | Mon 2/12/01 | 0%
2.5.9 | Project Management | 1 | Mon 3/5/01 | Mon 3/5/01 | 0%
2.5.10 | Project Management | 1 | Mon 3/26/01 | Mon 3/26/01 | 0%
2.5.11 | Project Management | 1 | Mon 4/16/01 | Mon 4/16/01 | 0%
2.5.12 | Project Management | 1 | Mon 5/7/01 | Mon 5/7/01 | 0%
2.5.13 | Project Management | 1 | Mon 5/28/01 | Mon 5/28/01 | 0%
2.5.14 | Project Management | 1 | Mon 6/18/01 | Mon 6/18/01 | 0%
2.5.15 | Project Management | 1 | Mon 7/9/01 | Mon 7/9/01 | 0%
2.5.16 | Project Management | 1 | Mon 7/30/01 | Mon 7/30/01 | 0%
2.5.17 | Project Management | 1 | Mon 8/20/01 | Mon 8/20/01 | 0%
2.5.18 | Project Management | 1 | Mon 9/10/01 | Mon 9/10/01 | 0%
2.5.19 | Project Management | 1 | Mon 10/1/01 | Mon 10/1/01 | 0%
2.5.20 | Project Management | 1 | Mon 10/22/01 | Mon 10/22/01 | 0%
2.5.21 | Project Management | 1 | Mon 11/12/01 | Mon 11/12/01 | 0%
2.5.22 | Project Management | 1 | Mon 12/3/01 | Mon 12/3/01 | 0%
2.5.23 | Project Management | 1 | Mon 12/24/01 | Mon 12/24/01 | 0%
2.5.24 | Project Management | 1 | Mon 1/14/02 | Mon 1/14/02 | 0%
2.5.25 | Project Management | 1 | Mon 2/4/02 | Mon 2/4/02 | 0%
2.5.26 | Project Management | 1 | Mon 2/25/02 | Mon 2/25/02 | 0%

## ID Days on Task
LearnCanada -Instructional Design
2.1 | Phase 1 Orientation & Team Formation | Name | Days
2.1.1 | ID Component Design
|  | ID Team Leader and EPS Site Leader | 5
2.1.2 | Verification of Focus, Tasks and Timelines
|  | OCDSB Site Leader | 1
|  | TDSB Site Leader | 1
|  | CSCV Site Leader | 1
|  | AESB Site Leader | 1
|  | KPR Site Leader | 1
|  | ID Team Leader and EPS Site Leader | 6 |  | 16
|  |  |  | 16 Total | 16
2.1.3 | Creation of Records and Resources
|  | ID Team Leader and EPS Site Leader | 6.5
|  | EPS Teachers | 5 |  | 12
|  |  |  | 12 Total | 12
2.1.4 | Event Planning
|  | ID Team Leader and EPS Site Leader | 20
|  | OCDSB Site Leader | 16
|  | TDSB Site Leader | 16
|  | CSCV Site Leader | 16
|  | AESB Site Leader | 16
|  | KPR Site Leader | 16
|  | EPS Teachers | 10
|  | OCDSB Teachers | 10
|  | KPRDSB Teachers | 10
|  | CSCV Teachers | 10
|  | AESB Teachers | 10
|  | TDSB Teachers | 10 |  | 160
|  |  |  | 160 Total | 160
2.1.5 | Teacher Coordination
|  | ID Team Leader and EPS Site Leader | 29
|  | OCDSB Site Leader | 10
|  | TDSB Site Leader | 10
|  | CSCV Site Leader | 10
|  | AESB Site Leader | 10
|  | KPR Site Leader | 10
|  | EPS Teachers | 10
|  | OCDSB Teachers | 10
|  | KPRDSB Teachers | 10
|  | CSCV Teachers | 10
|  | AESB Teachers | 10
|  | TDSB Teachers | 10 |  | 139
|  |  |  | 139 Total | 139
2.1.6 | Monthly Meetings
|  | ID Team Lead | 3
|  | OCDSB Site Leader | 3
|  | TDSB Site Leader | 3
|  | CSCV Site Leader | 3
|  | AESB Site Leader | 3
|  | KPR Site Leader | 3
|  | EPS Site Leader | 3 |  | 21
|  |  |  | 21 Total | 21
2.1.7 | Organization of Project Development
|  | ID Team Leader and EPS Site Leader | 16
|  | OCDSB Site Leader | 4
|  | TDSB Site Leader | 4
|  | CSCV Site Leader | 4
|  | AESB Site Leader | 4
|  | KPR Site Leader | 4
|  | EPS Teachers | 5
|  | OCDSB Teachers | 5
|  | KPRDSB Teachers | 5
|  | CSCV Teachers | 5
|  | AESB Teachers | 5
|  | TDSB Teachers | 5 |  | 66
|  |  |  | 66 Total | 66
2.1.8 | Collection of Resources
|  | ID Team Leader and EPS Site Leader | 5
|  | OCDSB Site Leader | 5
|  | TDSB Site Leader | 5
|  | CSCV Site Leader | 5
|  | AESB Site Leader | 5
|  | KPR Site Leader | 5
|  | EPS Teachers | 1
|  | OCDSB Teachers | 1
|  | KPRDSB Teachers | 1
|  | CSCV Teachers | 1
|  | AESB Teachers | 1
|  | TDSB Teachers | 1 |  | 36
|  |  |  | 36 Total | 36
2.1.9 | Identification of Project-Based Learning Projects
|  | ID Team Leader and EPS Site Leader | 5
|  | OCDSB Site Leader | 1
|  | TDSB Site Leader | 1
|  | CSCV Site Leader | 1
|  | AESB Site Leader | 1
|  | KPR Site Leader | 1
|  | EPS Teachers | 5
|  | OCDSB Teachers | 5
|  | KPRDSB Teachers | 5
|  | TDSB Teachers | 5
|  | CSCV Teachers | 5
|  | AESB Teachers | 5 |  | 40
|  |  |  | 40 Total | 40
2.1.10 | Ottawa Retreat
|  | ID Team Leader and EPS Site Leader | 3
|  | OCDSB Site Leader | 3
|  | TDSB Site Leader | 3
|  | CSCV Site Leader | 3
|  | AESB Site Leader | 3
|  | KPR Site Leader | 3
|  | EPS Teachers | 2
|  | OCDSB Teachers | 2
|  | KPRDSB Teachers | 2
|  | CSCV Teachers | 2
|  | AESB Teachers | 2
|  | TDSB Teachers | 2 |  | 30
|  |  |  | 30 Total | 30
2.2 | Phase 2: Requirements & Development
2.2.1 | Software Requirements
|  | ID Team Leader and EPS Site Leader | 0.5
|  | OCDSB Site Leader | 0.5
|  | TDSB Site Leader | 0.5
|  | CSCV Site Leader | 0.5
|  | AESB Site Leader | 0.5
|  | KPR Site Leader | 0.5
|  | EPS Teachers | 0.5
|  | OCDSB Teachers | 0.5
|  | KPRDSB Teachers | 0.5
|  | CSCV Teachers | 0.5
|  | AESB Teachers | 0.5
|  | TDSB Teachers | 0.5 |  | 6
|  |  |  | 6 Total | 6
2.2.2 | Assessment of content
|  | ID Team Leader and EPS Site Leader | 0.5
|  | OCDSB Site Leader | 0.5
|  | TDSB Site Leader | 0.5
|  | CSCV Site Leader | 0.5
|  | AESB Site Leader | 0.5
|  | KPR Site Leader | 0.5
|  | EPS Teachers | 0.5
|  | OCDSB Teachers | 0.5
|  | KPRDSB Teachers | 0.5
|  | CSCV Teachers | 0.5
|  | AESB Teachers | 0.5
|  | TDSB Teachers | 0.5 |  | 6
|  |  |  | 6 Total | 6
2.2.3 | Develop PBL Projects | ID Team Leader and EPS Site Leader | 5
|  | OCDSB Site Leader | 5
|  | TDSB Site Leader | 5
|  | CSCV Site Leader | 5
|  | AESB Site Leader | 5
|  | KPR Site Leader | 5
|  | EPS Teachers | 107
|  | OCDSB Teachers | 107
|  | KPRDSB Teachers | 107
|  | CSCV Teachers | 107
|  | AESB Teachers | 107
|  | TDSB Teachers | 107 |  | 672
|  |  |  | 672 Total | 672
2.2.4 | Conferences and Reports
|  | ID Team Leader and EPS Site Leader | 20
|  | EPS Site Leader | 29
|  | OCDSB Site Leader | 29
|  | TDSB Site Leader | 29
|  | CSCV Site Leader | 29
|  | AESB Site Leader | 29
|  | KPR Site Leader | 29
|  | EPS Teachers | 29
|  | OCDSB Teachers | 29
|  | KPRDSB Teachers | 29
|  | CSCV Teachers | 29
|  | AESB Teachers | 29
|  | TDSB Teachers | 29 |  | 368
|  |  |  | 368 Total | 368
2.2.5 | Program Evaluation | ID Team Leader and EPS Site Leader | 2
|  | TDSB Site Leader | 2
|  | EPS Site Leader | 2
|  | CSCV Site Leader | 2
|  | AESB Site Leader | 2
|  | KPR Site Leader | 2
|  | EPS Teachers | 5
|  | OCDSB Teachers | 5
|  | KPRDSB Teachers | 5
|  | CSCV Teachers | 5
|  | AESB Teachers | 5
|  | TDSB Teachers | 5 |  | 42
|  |  |  | 42 Total | 42
2.2.6 | CA*Net Conference - Infrastructure/Software Focus Group | ID Team Leader and EPS Site Leader | 1
|  | OCDSB Site Leader | 1
|  | TDSB Site Leader | 1
|  | CSCV Site Leader | 1
|  | AESB Site Leader | 1
|  | KPR Site Leader | 1
|  | EPS Teachers | 5
|  | OCDSB Teachers | 5
|  | KPRDSB Teachers | 5
|  | CSCV Teachers | 5
|  | AESB Teachers | 5
|  | TDSB Teachers | 5 |  | 36
|  |  |  | 36 Total | 36
2.2.7 | Evaulation/Modification of PBL Projects | ID Team Leader and EPS Site Leader | 2
|  | OCDSB Site Leader | 2
|  | TDSB Site Leader | 2
|  | CSCV Site Leader | 2
|  | AESB Site Leader | 2
|  | KPR Site Leader | 2
|  | EPS Teachers | 24
|  | OCDSB Teachers | 24
|  | KPRDSB Teachers | 24
|  | CSCV Teachers | 24
|  | AESB Teachers | 24
|  | TDSB Teachers | 24 |  | 156
|  |  |  | 156 Total | 156
2.3 | Phase 3: Deployment and Evaluation
2.3.1 | Modification of Objects | ID Team Leader and EPS Site Leader | 2
|  | OCDSB Site Leader | 2
|  | TDSB Site Leader | 2
|  | CSCV Site Leader | 2
|  | AESB Site Leader | 2
|  | KPR Site Leader | 2
|  | EPS Teachers | 20
|  | OCDSB Teachers | 20
|  | KPRDSB Teachers | 20
|  | CSCV Teachers | 20
|  | AESB Teachers | 20
|  | TDSB Teachers | 20 |  | 132
|  |  |  | 132 Total | 132
2.3.2 | Implementation of Projects | ID Team Leader and EPS Site Leader | 5
|  | OCDSB Site Leader | 1
|  | TDSB Site Leader | 1
|  | CSCV Site Leader | 1
|  | AESB Site Leader | 1
|  | KPR Site Leader | 1
|  | EPS Teachers | 30
|  | OCDSB Teachers | 30
|  | KPRDSB Teachers | 30
|  | CSCV Teachers | 30
|  | AESB Teachers | 30
|  | TDSB Teachers | 30 |  | 190
|  |  |  | 190 Total | 190
2.3.3 | Presentations - PD Day | ID Team Leader and EPS Site Leader | 1
|  | OCDSB Site Leader | 1
|  | TDSB Site Leader | 1
|  | KPR Site Leader | 1
|  | CSCV Site Leader | 1
|  | AESB Site Leader | 1
|  | OCDSB Teachers | 1
|  | EPS Teachers | 1
|  | TDSB Teachers | 1
|  | KPRDSB Teachers | 1
|  | AESB Teachers | 1
|  | CSCV Teachers | 1 |  | 12
|  |  |  | 12 Total | 12
2.3.4 | Presentations to other Groups | ID Team Leader and EPS Site Leader | 5
|  | OCDSB Site Leader | 3
|  | TDSB Site Leader | 3
|  | KPR Site Leader | 3
|  | CSCV Site Leader | 3
|  | AESB Site Leader | 3
|  | OCDSB Teachers | 1
|  | EPS Teachers | 1
|  | TDSB Teachers | 1
|  | KPRDSB Teachers | 1
|  | AESB Teachers | 1
|  | CSCV Teachers | 1 |  | 26
|  |  |  | 26 Total | 26
2.3.5 | CA*Net Conference - Outreach Efforts/Feedback | ID Team Leader and EPS Site Leader | 5
|  | TDSB Site Leader | 1
|  | OCDSB Site Leader | 1
|  | KPR Site Leader | 1
|  | CSCV Site Leader | 1
|  | AESB Site Leader | 1
|  | OCDSB Teachers | 5
|  | EPS Teachers | 5
|  | TDSB Teachers | 5
|  | KPRDSB Teachers | 5
|  | AESB Teachers | 5
|  | CSCV Teachers | 5 |  | 40
|  |  |  | 40 Total | 40
2.3.6 | CA*Net Conference - Evaluation of Infrastructure/Software | ID Team Leader and EPS Site Leader | 5
|  | TDSB Site Leader | 1
|  | OCDSB Site Leader | 1
|  | KPR Site Leader | 1
|  | CSCV Site Leader | 1
|  | AESB Site Leader | 1
|  | OCDSB Teachers | 5
|  | EPS Teachers | 5
|  | TDSB Teachers | 5
|  | KPRDSB Teachers | 5
|  | AESB Teachers | 5
|  | CSCV Teachers | 5 |  | 40
|  |  |  | 40 Total | 40
2.3.7 | Testing of Final Products | ID Team Leader and EPS Site Leader | 1
|  | TDSB Site Leader | 1
|  | OCDSB Site Leader | 1
|  | KPR Site Leader | 1
|  | CSCV Site Leader | 1
|  | AESB Site Leader | 1
|  | OCDSB Teachers | 5
|  | EPS Teachers | 5
|  | TDSB Teachers | 5
|  | KPRDSB Teachers | 5
|  | AESB Teachers | 5
|  | CSCV Teachers | 5 |  | 36
|  |  |  | 36 Total | 36
2.4 | Phase 4 Promotion / Expansion
2.4.1 | National Conference | ID Team Leader and EPS Site Leader | 2
|  | TDSB Site Leader | 2
|  | OCDSB Site Leader | 2
|  | KPR Site Leader | 2
|  | CSCV Site Leader | 2
|  | AESB Site Leader | 2
|  | OCDSB Teachers | 5
|  | EPS Teachers | 5
|  | TDSB Teachers | 5
|  | KPRDSB Teachers | 5
|  | AESB Teachers | 5
|  | CSCV Teachers | 5 |  | 42
|  |  |  | 42 Total | 42
2.4.2 | International Conference | ID Team Leader and EPS Site Leader | 2
|  | TDSB Site Leader | 2
|  | OCDSB Site Leader | 2
|  | KPR Site Leader | 2
|  | CSCV Site Leader | 2
|  | AESB Site Leader | 2
|  | OCDSB Teachers | 5
|  | EPS Teachers | 5
|  | TDSB Teachers | 5
|  | KPRDSB Teachers | 5
|  | AESB Teachers | 5
|  | CSCV Teachers | 5 |  | 42
|  |  |  | 42 Total | 42
2.5 | Project Management |  | 44 |  | 44
|  |  |  | 44 Total | 44
|  |  |  | Grand Total | 2410
|  | Total Days ID | 2409.5

## LearnCanada Task List
Project Start: Mon 7/17/00
Project Finish: Sun 3/31/02
Tasks
Task # | Task Name | Duration | Start | Finish | % Complete
| National Test Network | 391 days | Fri 9/15/00 | Fri 3/15/02 | 0%
| Phase I and II-National Test Network (Proof-of-Concept) | 174 days | Fri 9/15/00 | Wed 5/16/01 | 0%
| Requirements Definition | 79 days | Fri 9/15/00 | Wed 1/3/01 | 0%
| Define sites, types of nodes | 10 days | Fri 9/15/00 | Thu 9/28/00 | 0%
| Define network topology, minimum set of PSTs | 10 days | Thu 11/30/00 | Wed 12/13/00 | 0%
| Define software packages | 15 days | Thu 12/14/00 | Wed 1/3/01 | 0%
| Phase I-Limited Deployment with Basic PSTs | 32 days | Thu 1/4/01 | Fri 2/16/01 | 0%
| Scope Definition | 2 days | Thu 1/4/01 | Fri 1/5/01 | 0%
| Implementation and Test | 27 days | Mon 1/8/01 | Tue 2/13/01 | 0%
| Acquisition of Equipment | 20 days | Mon 1/8/01 | Fri 2/2/01 | 0%
| Equipment configuration | 5 days | Mon 2/5/01 | Fri 2/9/01 | 0%
| Integration and test of system | 2 days | Mon 2/12/01 | Tue 2/13/01 | 0%
| Verification of network connectivity | 0 days | Tue 2/13/01 | Tue 2/13/01 | 0%
| Performance Evaluation | 3 days | Wed 2/14/01 | Fri 2/16/01 | 0%
| Definition of metrics | 1 day | Wed 2/14/01 | Wed 2/14/01 | 0%
| Develop test plan | 1 day | Thu 2/15/01 | Thu 2/15/01 | 0%
| Conduct test and perform measurements | 1 day | Fri 2/16/01 | Fri 2/16/01 | 0%
| Phase II- Evolving NTN and Advanced PSTs | 63 days | Mon 2/19/01 | Wed 5/16/01 | 0%
| Additon of new nodes | 5 days | Mon 2/19/01 | Fri 2/23/01 | 0%
| All 6 School Boards connected to CA*Net 3 | 0 days | Thu 2/22/01 | Thu 2/22/01 | 0%
| Incorporation of Validation and Recommended PSTs | 60 days | Thu 2/22/01 | Wed 5/16/01 | 0%
| Ongoing Performance Evaluation | 60 days | Mon 2/19/01 | Fri 5/11/01 | 0%
| Phase III -Controlled Experimental Testbed | 79 days | Thu 5/17/01 | Tue 9/4/01 | 0%
| Requirements Definition | 47 days | Thu 5/17/01 | Tue 8/21/01 | 0%
| Detailed Design | 5 days | Wed 8/22/01 | Tue 8/28/01 | 0%
| Implementation and Test | 4 days | Wed 8/29/01 | Mon 9/3/01 | 0%
| Acquisition of new equipment and software | 1 day | Wed 8/29/01 | Wed 8/29/01 | 0%
| Equipment configuration and installation of software | 1 day | Thu 8/30/01 | Thu 8/30/01 | 0%
| Integration and test system | 1 day | Fri 8/31/01 | Fri 8/31/01 | 0%
| Verification of network connectivity | 1 day | Mon 9/3/01 | Mon 9/3/01 | 0%
Old | PST Validation and Test | 4 days | Thu 8/30/01 | Tue 9/4/01 | 0%
| Scope extent of PST implementation | 1 day | Thu 8/30/01 | Thu 8/30/01 | 0%
| Develop test plan | 1 day | Fri 8/31/01 | Fri 8/31/01 | 0%
| Conduct testing | 1 day | Mon 9/3/01 | Mon 9/3/01 | 0%
| Recommend for migration to NTN | 1 day | Tue 9/4/01 | Tue 9/4/01 | 0%
| Operations and Maintenance | 318 days | Fri 9/15/00 | Tue 12/4/01 | 0%
| Technical Web site | 318 days | Fri 9/15/00 | Tue 12/4/01 | 0%
| Development of a NOC - National Operation Centre | 40 days | Mon 2/19/01 | Fri 4/13/01 | 0%
| Testing and Troubleshooting | 40 days | Mon 4/16/01 | Fri 6/8/01 | 0%
| Training fro technical leads in each Board | 10 days | Mon 6/11/01 | Fri 6/22/01 | 0%
| Schedule Events | 10 days | Mon 6/25/01 | Fri 7/6/01 | 0%
| Reporting/project management | 391 days | Fri 9/15/00 | Fri 3/15/02 | 0%
| Meetings | 371 days | Fri 9/15/00 | Fri 2/15/02 | 0%
| Kickoff | 1 day | Fri 9/15/00 | Fri 9/15/00 | 0%
| Monthly Meetings | 316 days | Mon 9/18/00 | Mon 12/3/01 | 0%
| Monthly Meeting | 1 day | Mon 9/18/00 | Mon 9/18/00 | 0%
| Monthly Meeting | 1 day | Mon 10/2/00 | Mon 10/2/00 | 0%
| Monthly Meeting | 1 day | Mon 11/6/00 | Mon 11/6/00 | 0%
| Monthly Meeting | 1 day | Mon 12/4/00 | Mon 12/4/00 | 0%
| Monthly Meeting | 1 day | Mon 1/1/01 | Mon 1/1/01 | 0%
| Monthly Meeting | 1 day | Mon 2/5/01 | Mon 2/5/01 | 0%
| Monthly Meeting | 1 day | Mon 3/5/01 | Mon 3/5/01 | 0%
| Monthly Meeting | 1 day | Mon 4/2/01 | Mon 4/2/01 | 0%
| Monthly Meeting | 1 day | Mon 5/7/01 | Mon 5/7/01 | 0%
| Monthly Meeting | 1 day | Mon 6/4/01 | Mon 6/4/01 | 0%
| Monthly Meeting | 1 day | Mon 7/2/01 | Mon 7/2/01 | 0%
| Monthly Meeting | 1 day | Mon 8/6/01 | Mon 8/6/01 | 0%
| Monthly Meeting | 1 day | Mon 9/3/01 | Mon 9/3/01 | 0%
| Monthly Meeting | 1 day | Mon 10/1/01 | Mon 10/1/01 | 0%
| Monthly Meeting | 1 day | Mon 11/5/01 | Mon 11/5/01 | 0%
| Monthly Meeting | 1 day | Mon 12/3/01 | Mon 12/3/01 | 0%
| Monthly progress reviews | 1 day | Fri 9/15/00 | Fri 9/15/00 | 0%
| Presentations | 371 days | Fri 9/15/00 | Fri 2/15/02 | 0%
| Presentations 1 | 1 day | Fri 9/15/00 | Fri 9/15/00 | 0%
| Presentations 2 | 1 day | Fri 10/13/00 | Fri 10/13/00 | 0%
| Presentations 3 | 1 day | Fri 11/17/00 | Fri 11/17/00 | 0%
| Presentations 4 | 1 day | Fri 12/15/00 | Fri 12/15/00 | 0%
| Presentations 5 | 1 day | Fri 1/19/01 | Fri 1/19/01 | 0%
| Presentations 6 | 1 day | Fri 2/16/01 | Fri 2/16/01 | 0%
| Presentations 7 | 1 day | Fri 3/16/01 | Fri 3/16/01 | 0%
| Presentations 8 | 1 day | Fri 4/13/01 | Fri 4/13/01 | 0%
| Presentations 9 | 1 day | Fri 5/18/01 | Fri 5/18/01 | 0%
| Presentations 10 | 1 day | Fri 6/15/01 | Fri 6/15/01 | 0%
| Presentations 11 | 1 day | Fri 7/13/01 | Fri 7/13/01 | 0%
| Presentations 12 | 1 day | Fri 8/17/01 | Fri 8/17/01 | 0%
| Presentations 13 | 1 day | Fri 9/21/01 | Fri 9/21/01 | 0%
| Presentations 14 | 1 day | Mon 10/15/01 | Mon 10/15/01 | 0%
| Presentations 15 | 1 day | Fri 11/16/01 | Fri 11/16/01 | 0%
| Presentations 20 | 1 day | Fri 12/14/01 | Fri 12/14/01 | 0%
| Presentations 21 | 1 day | Fri 1/18/02 | Fri 1/18/02 | 0%
| Presentations 22 | 1 day | Fri 2/15/02 | Fri 2/15/02 | 0%
| Final Technical Acceptance Demo | 0 days | Tue 1/1/02 | Tue 1/1/02 | 0%
| Documentation | 391 days | Fri 9/15/00 | Fri 3/15/02 | 0%
| Monthly Reports | 337 days | Thu 11/30/00 | Fri 3/15/02 | 0%
| Monthly Reports 3 | 1 day | Thu 11/30/00 | Thu 11/30/00 | 0%
| Monthly Reports 4 | 1 day | Fri 12/29/00 | Fri 12/29/00 | 0%
| Monthly Reports 5 | 1 day | Wed 1/31/01 | Wed 1/31/01 | 0%
| Monthly Reports 6 | 1 day | Wed 2/28/01 | Wed 2/28/01 | 0%
| Monthly Reports 7 | 1 day | Fri 3/30/01 | Fri 3/30/01 | 0%
| Monthly Reports 8 | 1 day | Mon 4/30/01 | Mon 4/30/01 | 0%
| Monthly Reports 9 | 1 day | Thu 5/31/01 | Thu 5/31/01 | 0%
| Monthly Reports 10 | 1 day | Fri 6/29/01 | Fri 6/29/01 | 0%
| Monthly Reports 11 | 1 day | Tue 7/31/01 | Tue 7/31/01 | 0%
| Monthly Reports 12 | 1 day | Fri 8/31/01 | Fri 8/31/01 | 0%
| Monthly Reports 13 | 1 day | Fri 9/28/01 | Fri 9/28/01 | 0%
| Monthly Reports 14 | 1 day | Wed 10/31/01 | Wed 10/31/01 | 0%
| Monthly Reports 15 | 1 day | Fri 11/30/01 | Fri 11/30/01 | 0%
| Monthly Reports 16 | 1 day | Mon 12/31/01 | Mon 12/31/01 | 0%
| Monthly Reports 17 | 1 day | Thu 1/31/02 | Thu 1/31/02 | 0%
| Monthly Reports 18 | 1 day | Thu 2/28/02 | Thu 2/28/02 | 0%
| Monthly Reports 19 | 1 day | Fri 3/15/02 | Fri 3/15/02 | 0%
| Presentation Material | 4 days | Fri 9/15/00 | Wed 9/20/00 | 0%
| Prepare Phase 1 Report | 4 days | Mon 12/18/00 | Thu 12/21/00 | 0%
| Issues Phase 1 Report | 4 days | Fri 12/22/00 | Wed 12/27/00 | 0%
| Prepare Phase 2 Report | 4 days | Thu 5/17/01 | Tue 5/22/01 | 0%
| Issues Phase 2 Report | 4 days | Wed 5/23/01 | Mon 5/28/01 | 0%
| Prepare Phase 3 Report | 4 days | Wed 9/5/01 | Mon 9/10/01 | 0%
| Issue Phase 3 report | 4 days | Tue 9/11/01 | Fri 9/14/01 | 0%
| Prepare Executive Summary | 8 days | Tue 1/1/02 | Thu 1/10/02 | 0%
| Issue Executive Summary | 0 days | Mon 2/4/02 | Mon 2/4/02 | 0%
| Report at International conference | 0 days | Mon 2/4/02 | Mon 2/4/02 | 0%
| Project Management | 0 days | Mon 2/4/02 | Mon 2/4/02 | 0%
2.0 | LearnCanada - Instructional Design | 377 days | Fri 9/15/00 | Mon 2/25/02 | 0%
2.1 | Phase 1 - Orientation and Team Forming | 61 days | Fri 9/15/00 | Fri 12/8/00 | 0%
2.1.1 | I.D. Component Design | 5 days | Fri 9/15/00 | Thu 9/21/00 | 0%
2.1.2 | Verification of Focus, Tasks and Timelines | 1 day | Fri 9/22/00 | Fri 9/22/00 | 0%
2.1.3 | Creation of Records and Resources | 5 days | Mon 9/25/00 | Fri 9/29/00 | 0%
2.1.4 | Event planning | 5 days | Mon 10/2/00 | Fri 10/6/00 | 0%
2.1.5 | Teacher coordination | 5 days | Mon 10/2/00 | Fri 10/6/00 | 0%
| CA*Net Conference Event: Team Building | 0 days | Fri 10/6/00 | Fri 10/6/00 | 0%
2.1.6 | Conference completed | 0 days | Fri 10/6/00 | Fri 10/6/00 | 0%
2.1.7 | Organization of Project Development | 20 days | Mon 10/9/00 | Fri 11/3/00 | 0%
2.1.8 | Collection of Resources | 20 days | Mon 11/6/00 | Fri 12/1/00 | 0%
2.1.9 | Identification of Project-based learning Projects | 5 days | Mon 12/4/00 | Fri 12/8/00 | 0%
2.2 | Phase 2 - Requirement Definition and Development | 259.88 days | Fri 9/15/00 | Thu 9/13/01 | 0%
2.2.1 | Definition of Software Requirements | 5 days | Fri 9/15/00 | Thu 9/21/00 | 0%
2.2.2 | Assessment of Exisiting Content | 10 days | Fri 9/22/00 | Thu 10/5/00 | 0%
2.2.3 | Ottawa Retreat | 2 days | Thu 10/12/00 | Fri 10/13/00 | 0%
2.2.4 | Develop Project-based Learning(PBL) Resources Sept 2000-June 2001 | 126 days | Mon 10/30/00 | Mon 4/23/01 | 0%
2.2.4.1 | On-line Session | 1 day | Mon 10/30/00 | Mon 10/30/00 | 0%
2.2.4.2 | Small Group On-line | 1 day | Thu 11/16/00 | Thu 11/16/00 | 0%
2.2.4.3 | On-line Session | 1 day | Tue 11/21/00 | Tue 11/21/00 | 0%
2.2.4.4 | On-line Conference #2 | 1 day | Thu 11/30/00 | Thu 11/30/00 | 0%
2.2.4.5 | Lead Report #1 Due | 1 day | Fri 12/1/00 | Fri 12/1/00 | 0%
2.2.4.6 | On-line Conference #3 | 1 day | Thu 12/14/00 | Thu 12/14/00 | 0%
2.2.4.7 | Lead Report #2 Due | 0 days | Fri 12/22/00 | Fri 12/22/00 | 0%
2.2.4.8 | Small Group on-line | 1 day | Thu 1/18/01 | Thu 1/18/01 | 0%
2.2.4.9 | Small Group on-line | 1 day | Thu 1/25/01 | Thu 1/25/01 | 0%
2.2.4.10 | Lead Report #3 due | 1 day | Wed 1/31/01 | Wed 1/31/01 | 0%
2.2.4.11 | On-line Conference #4 | 1 day | Thu 2/8/01 | Thu 2/8/01 | 0%
2.2.4.12 | Small Group on-line | 1 day | Thu 2/15/01 | Thu 2/15/01 | 0%
2.2.4.13 | Lead Report #4 Due | 1 day | Wed 2/28/01 | Wed 2/28/01 | 0%
2.2.4.14 | On-line Conference $5 | 1 day | Thu 3/1/01 | Thu 3/1/01 | 0%
2.2.4.15 | Small Group on-line | 1 day | Thu 3/15/01 | Thu 3/15/01 | 0%
2.2.4.16 | Lead Report #5 Due | 1 day | Fri 3/30/01 | Fri 3/30/01 | 0%
2.2.4.17 | On-line Conference #6 | 1 day | Thu 4/5/01 | Thu 4/5/01 | 0%
2.2.4.18 | Small Group on-line | 1 day | Thu 4/19/01 | Thu 4/19/01 | 0%
2.2.4.19 | Lead Report #7 due | 1 day | Fri 4/20/01 | Fri 4/20/01 | 0%
2.2.4.20 | Develop Project-based Learning(PBL) Resources Sept 2001-Jan 2002 | 1 day | Mon 4/23/01 | Mon 4/23/01 | 0%
2.2.4.20.1 | TBA | 1 day | Mon 4/23/01 | Mon 4/23/01 | 0%
2.2.5 | Program Evaluation | 30 days | Wed 11/1/00 | Thu 9/13/01 | 0%
2.2.6 | CA*Net Conference :Infrastructure/Conference Focus Group | 0 days | Mon 1/1/01 | Mon 1/1/01 | 0%
2.2.6.1 | Conference completed | 0 days | Mon 1/1/01 | Mon 1/1/01 | 0%
2.2.7 | Evaluation/Modification of PBL Projects | 30 days | Mon 1/1/01 | Fri 2/9/01 | 0%
2.3 | Phase 3 - Deployment and Evaluation | 76 days | Thu 9/13/01 | Fri 12/28/01 | 0%
2.3.1 | Modification of Objects | 20 days | Thu 9/13/01 | Thu 10/11/01 | 0%
2.3.2 | Implementation of Projects | 30 days | Thu 10/11/01 | Thu 11/22/01 | 0%
2.3.3 | Presentations- PD Day | 1 day | Thu 11/22/01 | Fri 11/23/01 | 0%
2.3.4 | Presentations to Other Groups | 10 days | Fri 11/23/01 | Fri 12/7/01 | 0%
2.3.5 | CA*Net Conference/Outreach Efforts/Feedback | 5 days | Fri 12/7/01 | Fri 12/14/01 | 0%
2.3.6 | CA*Net Conference Evaluation of Infrastructure/Software | 5 days | Fri 12/14/01 | Fri 12/21/01 | 0%
2.3.7 | Testing of Final Products | 5 days | Fri 12/21/01 | Fri 12/28/01 | 0%
2.4 | Phase 4 - Promotion/ Expansion Acitivities | 103 days | Mon 10/1/01 | Wed 2/20/02 | 0%
2.4.1 | National Conference | 5 days | Mon 10/1/01 | Fri 10/5/01 | 0%
2.4.2 | International Conference | 5 days | Thu 2/14/02 | Wed 2/20/02 | 0%
2.4.2.1 | International Conference Report Preparation | 5 days | Thu 2/14/02 | Wed 2/20/02 | 0%
2.4.2.2 | Conference delivery of Report | 0 days | Wed 2/20/02 | Wed 2/20/02 | 0%
2.5 | Project Management | 376 days | Mon 9/18/00 | Mon 2/25/02 | 0%
2.5.1 | Project Management | 1 day | Mon 9/18/00 | Mon 9/18/00 | 0%
2.5.2 | Project Management | 1 day | Mon 10/9/00 | Mon 10/9/00 | 0%
2.5.3 | Project Management | 1 day | Mon 10/30/00 | Mon 10/30/00 | 0%
2.5.4 | Project Management | 1 day | Mon 11/20/00 | Mon 11/20/00 | 0%
2.5.5 | Project Management | 1 day | Mon 12/11/00 | Mon 12/11/00 | 0%
2.5.6 | Project Management | 1 day | Mon 1/1/01 | Mon 1/1/01 | 0%
2.5.7 | Project Management | 1 day | Mon 1/22/01 | Mon 1/22/01 | 0%
2.5.8 | Project Management | 1 day | Mon 2/12/01 | Mon 2/12/01 | 0%
2.5.9 | Project Management | 1 day | Mon 3/5/01 | Mon 3/5/01 | 0%
2.5.10 | Project Management | 1 day | Mon 3/26/01 | Mon 3/26/01 | 0%
2.5.11 | Project Management | 1 day | Mon 4/16/01 | Mon 4/16/01 | 0%
2.5.12 | Project Management | 1 day | Mon 5/7/01 | Mon 5/7/01 | 0%
2.5.13 | Project Management | 1 day | Mon 5/28/01 | Mon 5/28/01 | 0%
2.5.14 | Project Management | 1 day | Mon 6/18/01 | Mon 6/18/01 | 0%
2.5.15 | Project Management | 1 day | Mon 7/9/01 | Mon 7/9/01 | 0%
2.5.16 | Project Management | 1 day | Mon 7/30/01 | Mon 7/30/01 | 0%
2.5.17 | Project Management | 1 day | Mon 8/20/01 | Mon 8/20/01 | 0%
2.5.18 | Project Management | 1 day | Mon 9/10/01 | Mon 9/10/01 | 0%
2.5.19 | Project Management | 1 day | Mon 10/1/01 | Mon 10/1/01 | 0%
2.5.20 | Project Management | 1 day | Mon 10/22/01 | Mon 10/22/01 | 0%
2.5.21 | Project Management | 1 day | Mon 11/12/01 | Mon 11/12/01 | 0%
2.5.22 | Project Management | 1 day | Mon 12/3/01 | Mon 12/3/01 | 0%
2.5.23 | Project Management | 1 day | Mon 12/24/01 | Mon 12/24/01 | 0%
2.5.24 | Project Management | 1 day | Mon 1/14/02 | Mon 1/14/02 | 0%
2.5.25 | Project Management | 1 day | Mon 2/4/02 | Mon 2/4/02 | 0%
2.5.26 | Project Management | 1 day | Mon 2/25/02 | Mon 2/25/02 | 0%
| LearnCanada - Software Multimedia Development | 306 days | Fri 9/15/00 | Fri 11/16/01 | 0%
| Phase 1 - Defiintion of Requirements | 70 days | Fri 9/15/00 | Thu 12/21/00 | 0%
| Software usability focus groups | 7 days | Fri 9/15/00 | Mon 9/25/00 | 0%
| Review COTS software | 20 days | Fri 9/15/00 | Thu 10/12/00 | 0%
| Define software requirements | 20 days | Fri 10/13/00 | Thu 11/9/00 | 0%
| Review existing video and multimedia content | 30 days | Fri 9/15/00 | Thu 10/26/00 | 0%
| Define multimedia content requirements | 40 days | Fri 10/27/00 | Thu 12/21/00 | 0%
| Phase 2 - Development | 188 days | Fri 12/22/00 | Tue 9/11/01 | 0%
| Develop and test portal repository software | 60 days | Fri 12/22/00 | Thu 3/15/01 | 0%
| Develop and test multimedia software | 125 days | Fri 12/22/00 | Thu 7/12/01 | 0%
| Develop and test software and content | 100 days | Fri 12/22/00 | Thu 5/10/01 | 0%
| Select and Digitize Video Content | 50 days | Fri 12/22/00 | Thu 3/1/01 | 0%
| Develop Multimedia Access andReconfigurability Method | 50 days | Fri 3/2/01 | Thu 5/10/01 | 0%
| Develop and test multimedia databases | 55 days | Fri 12/22/00 | Thu 3/8/01 | 0%
| Full integration and testing | 117 days | Mon 2/26/01 | Tue 9/11/01 | 0%
| Phase 3 - Field trials, Deployment and Evaluation | 261 days | Wed 11/1/00 | Thu 11/1/01 | 0%
| Professional Development Field Test | 261 days | Wed 11/1/00 | Thu 11/1/01 | 0%
| Professional Development Field Trials | 129 days | Wed 11/1/00 | Wed 10/10/01 | 0%
| Deliver Alpha product | 0 days | Thu 2/1/01 | Thu 2/1/01 | 0%
| Deliver Beta Product | 0 days | Tue 5/1/01 | Tue 5/1/01 | 0%
| Deliver Final Prototype | 0 days | Thu 11/1/01 | Thu 11/1/01 | 0%
| Recommendations for future software content | 25 days | Fri 6/1/01 | Thu 7/5/01 | 0%
| Final report & International conference | 16 days | Mon 10/1/01 | Mon 10/22/01 | 0%
| Project Meetings | 306 days | Fri 9/15/00 | Fri 11/16/01 | 0%
| Meeting | 1 day | Fri 9/15/00 | Fri 9/15/00 | 0%
| Meeting | 1 day | Fri 10/13/00 | Fri 10/13/00 | 0%
| Meeting | 1 day | Fri 11/17/00 | Fri 11/17/00 | 0%
| Meeting | 1 day | Fri 12/15/00 | Fri 12/15/00 | 0%
| Meeting | 1 day | Fri 1/12/01 | Fri 1/12/01 | 0%
| Meeting | 1 day | Mon 4/16/01 | Mon 4/16/01 | 0%
| Meeting | 1 day | Mon 5/21/01 | Mon 5/21/01 | 0%
| Meeting | 1 day | Fri 4/13/01 | Fri 4/13/01 | 0%
| Meeting | 1 day | Fri 5/18/01 | Fri 5/18/01 | 0%
| Meeting | 1 day | Fri 5/18/01 | Fri 5/18/01 | 0%
| Meeting | 1 day | Fri 6/15/01 | Fri 6/15/01 | 0%
| Meeting | 1 day | Fri 7/13/01 | Fri 7/13/01 | 0%
| Meeting | 1 day | Fri 8/17/01 | Fri 8/17/01 | 0%
| Meeting | 1 day | Fri 9/14/01 | Fri 9/14/01 | 0%
| Meeting | 1 day | Fri 10/19/01 | Fri 10/19/01 | 0%
| Meeting | 1 day | Fri 11/16/01 | Fri 11/16/01 | 0%
| Learn Canada - Development of A Virtual Community | 380 days | Fri 9/15/00 | Fri 3/1/02 | 0%
| Sustainability Requirements | 141 days | Fri 9/15/00 | Sun 4/1/01 | 0%
| Development of Strategic Plan | 10 days | Wed 11/1/00 | Tue 11/14/00 | 0%
| Define Scope and Outline of Report | 1 day | Wed 11/1/00 | Wed 11/1/00 | 0%
| Research and Collect Appropriate Data | 2 days | Thu 11/2/00 | Fri 11/3/00 | 0%
| Write Draft Report | 3 days | Mon 11/6/00 | Wed 11/8/00 | 0%
| Provide Draft Report to All Founding Members for Input | 1 day | Thu 11/9/00 | Thu 11/9/00 | 0%
| Make Revisions as Requested | 2 days | Fri 11/10/00 | Mon 11/13/00 | 0%
| Produce Final Report | 1 day | Tue 11/14/00 | Tue 11/14/00 | 0%
| Send Final Report to All founding Members and Lead Contractor | 0 days | Tue 11/14/00 | Tue 11/14/00 | 0%
| Development of Business Plan | 42 days | Thu 11/2/00 | Mon 1/1/01 | 0%
| Define Scope and Outline of Report | 1 day | Thu 11/2/00 | Thu 11/2/00 | 0%
| Research and Collect Appropriate Data | 2 days | Fri 11/3/00 | Mon 11/6/00 | 0%
| Write Draft Report | 3 days | Tue 11/7/00 | Thu 11/9/00 | 0%
| Provide Draft Report to All Founding Members for Input | 1 day | Fri 11/10/00 | Fri 11/10/00 | 0%
| Make Revisions as Requested | 2 days | Mon 11/13/00 | Tue 11/14/00 | 0%
| Produce Final Report | 1 day | Wed 11/15/00 | Wed 11/15/00 | 0%
| Send Final Report to All founding Members and Lead Contractor | 0 days | Mon 1/1/01 | Mon 1/1/01 | 0%
| Development of Marketing Plan | 108 days | Wed 11/1/00 | Sun 4/1/01 | 0%
| Define Scope and Outline of Report | 0.5 days | Wed 11/1/00 | Wed 11/1/00 | 0%
| Research and Collect Appropriate Data | 1 day | Wed 11/1/00 | Thu 11/2/00 | 0%
| Write Draft Report | 1 day | Thu 11/2/00 | Fri 11/3/00 | 0%
| Provide Draft Report to All Founding Members for Input | 1 day | Fri 12/1/00 | Fri 12/1/00 | 0%
| Make Revisions as Requested | 0.5 days | Mon 12/4/00 | Mon 12/4/00 | 0%
| Produce Final Report | 1 day | Mon 12/4/00 | Tue 12/5/00 | 0%
| Send Final Report to All founding Members and Lead Contractor | 0 days | Sun 4/1/01 | Sun 4/1/01 | 0%
| Define teacher requirements for creating and sustainining PD within a Broadband Enabled Learning Environment | 111 days | Fri 9/15/00 | Fri 2/16/01 | 0%
| Consult with Particpating Teachers in all Boards to Define the Application Needs | 2 days | Fri 9/15/00 | Mon 9/18/00 | 0%
| Deliver Data to CRC and NRC for inclusion in the development phase | 1 day | Mon 1/1/01 | Mon 1/1/01 | 0%
| Review Quarterly for feedback and adjustment | 2 days | Wed 2/14/01 | Thu 2/15/01 | 0%
| Research off-the-shelf solutions that may meet requirments. | 1 day | Fri 2/16/01 | Fri 2/16/01 | 0%
| Phase 2 - Relationship Building | 271.88 days | Fri 9/15/00 | Mon 10/1/01 | 0%
| Develop Communications Policies and Procedures -Coordinate Founding Members Steering Committee Meetings | 271.88 days | Fri 9/15/00 | Mon 10/1/01 | 0%
| Coordinate founding member steering committee meetings | 10 days | Fri 9/15/00 | Mon 10/1/01 | 0%
| Collaborate with other Canarie Projects | 10 days | Fri 9/15/00 | Mon 7/2/01 | 0%
| Consolidate and/or expand associate partners and contributions, | 10 days | Fri 9/15/00 | Mon 10/1/01 | 0%
| Create Web Site Content and P.R. Material, Communicate with Ministries, Teachers Association and Colleges | 5 days | Fri 9/15/00 | Thu 12/21/00 | 0%
| Create synergy with other government learning inititatives | 10 days | Fri 9/15/00 | Fri 6/29/01 | 0%
| Select and negotiate MOU with other International Partners | 10 days | Fri 9/15/00 | Thu 9/28/00 | 0%
| Negotiate MoUs with selected Partners on behalf of consortium | 10 days | Fri 9/15/00 | Thu 9/28/00 | 0%
| Develop Team Building Strategies and Events | 5 days | Fri 9/15/00 | Thu 9/21/00 | 0%
| Requirements Definition | 318 days | Fri 9/15/00 | Tue 12/4/01 | 0%
| Review of Literature-Virtual Learning Communities | 10 days | Fri 9/15/00 | Thu 12/28/00 | 0%
| Evaluation of the barriers and solutions to cross sectoral/cross regional partnerships | 7 days | Fri 9/15/00 | Tue 12/26/00 | 0%
| Prepare Report LearnCanada - A Case Study | 285 days | Wed 11/1/00 | Tue 12/4/01 | 0%
| Define Scope and Outline of Report | 1 day | Wed 11/1/00 | Wed 11/1/00 | 0%
| Research and Collect Appropriate Data | 1 day | Thu 11/2/00 | Thu 11/2/00 | 0%
| Write Draft Report | 1 day | Tue 11/14/00 | Tue 11/14/00 | 0%
| Provide Draft Report to All Founding Members for Input | 1 day | Tue 1/23/01 | Tue 1/23/01 | 0%
| Make Revisions as Requested | 2 days | Wed 2/21/01 | Thu 2/22/01 | 0%
| Produce Final Report | 4 days | Thu 11/29/01 | Tue 12/4/01 | 0%
| Send Final Report to All founding Members and Lead Contractor | 0 days | Tue 12/4/01 | Tue 12/4/01 | 0%
| Phase 3 - Deployment and Evaluation | 380 days | Fri 9/15/00 | Fri 3/1/02 | 0%
| Producer: Management of all Virtual Encounters | 25 days | Fri 9/15/00 | Mon 5/7/01 | 0%
| Plan and Implement 3 National/International P.D. Sessions | 130 days | Wed 11/1/00 | Tue 5/1/01 | 0%
| Plan event #1 | 6 days | Wed 11/1/00 | Wed 11/8/00 | 0%
| Deliver Session | 1 day | Thu 11/9/00 | Thu 11/9/00 | 0%
| Report of Session to Founding Members | 0 days | Thu 11/9/00 | Thu 11/9/00 | 0%
| Plan event #2 | 6 days | Fri 11/10/00 | Fri 11/17/00 | 0%
| Deliver Session | 2 days | Mon 1/1/01 | Tue 1/2/01 | 0%
| Report of Session to Founding Members | 0 days | Tue 1/2/01 | Tue 1/2/01 | 0%
| Plan event #3 | 6 days | Thu 2/1/01 | Thu 2/8/01 | 0%
| Deliver Session | 1 day | Tue 5/1/01 | Tue 5/1/01 | 0%
| Report of Session to Founding Members | 0 days | Tue 5/1/01 | Tue 5/1/01 | 0%
| Host a National/Iinternational P.D. Virtual Conference | 34 days | Mon 1/14/02 | Fri 3/1/02 | 0%
| Host event | 16 days | Mon 1/14/02 | Mon 2/4/02 | 0%
| Report of Session to Founding Members | 0 days | Fri 3/1/02 | Fri 3/1/02 | 0%
| Conference Report Delivered | 0 days | Fri 3/1/02 | Fri 3/1/02 | 0%
| External Evaluation | 382 days | Fri 9/15/00 | Mon 3/4/02 | 0%
| Literature Review | 10 days | Fri 9/15/00 | Thu 9/28/00 | 0%
| Development of Evaluation Plan | 28 days | Fri 9/29/00 | Tue 11/7/00 | 0%
| On-site Evaluation Team Meeting | 2 days | Fri 9/29/00 | Mon 10/2/00 | 0%
| Project Team Leaders Evaluation Meeting | 2 days | Tue 10/3/00 | Wed 10/4/00 | 0%
| Full Project Retreat | 2 days | Thu 10/5/00 | Fri 10/6/00 | 0%
| Validate Evaluation within Individual Work Packages | 5 days | Mon 10/9/00 | Fri 10/13/00 | 0%
| Establish Evaluation Benchmarks within and amongst Individual Workplans | 5 days | Mon 10/16/00 | Fri 10/20/00 | 0%
| Review Evaluation Plans with On-site Teams | 5 days | Mon 10/23/00 | Fri 10/27/00 | 0%
| Review Evaluation Plans with Teacher Focus Groups | 5 days | Mon 10/30/00 | Fri 11/3/00 | 0%
| Initial Development of Evaluation Tools | 1 day | Mon 11/6/00 | Mon 11/6/00 | 0%
| Validate Evaluation Plans with Team Leaders | 1 day | Tue 11/7/00 | Tue 11/7/00 | 0%
| Implementation Cycle 1(Nov-Jan 15, 2001) | 27 days | Wed 11/8/00 | Thu 12/14/00 | 0%
| Collect Data and Analyze Results | 5 days | Wed 11/8/00 | Tue 11/14/00 | 0%
| Review Evaluation Results with Team Leaders | 5 days | Wed 11/15/00 | Tue 11/21/00 | 0%
| Produce Draft Report | 5 days | Wed 11/22/00 | Tue 11/28/00 | 0%
| Collect and Review Feedback from Multiple Review Groups | 5 days | Wed 11/29/00 | Tue 12/5/00 | 0%
| Make Required Modifications | 5 days | Wed 12/6/00 | Tue 12/12/00 | 0%
| Validate Revisions and Distribute Report | 2 days | Wed 12/13/00 | Thu 12/14/00 | 0%
| Validate Revisions | 2 days | Wed 12/13/00 | Thu 12/14/00 | 0%
| leiver report to Stemnet | 0 days | Thu 12/14/00 | Thu 12/14/00 | 0%
| Implementation Cycle 2 (Jan 15-June 30, 2001) | 42 days | Mon 1/15/01 | Tue 3/13/01 | 0%
| Update Evaluation tools | 10 days | Mon 1/15/01 | Fri 1/26/01 | 0%
| Distribute Evaluation Tools | 5 days | Mon 1/29/01 | Fri 2/2/01 | 0%
| Collect Data and Analyze Results | 5 days | Mon 2/5/01 | Fri 2/9/01 | 0%
| Review Evaluation Results with Team Leaders | 5 days | Mon 2/12/01 | Fri 2/16/01 | 0%
| Produce Draft Report | 5 days | Mon 2/19/01 | Fri 2/23/01 | 0%
| Collect and Review Feedback from Multiple Review Groups | 5 days | Mon 2/26/01 | Fri 3/2/01 | 0%
| Make Required Modifications | 5 days | Mon 3/5/01 | Fri 3/9/01 | 0%
| Validate Revisions and Distrinute Report | 2 days | Mon 3/12/01 | Tue 3/13/01 | 0%
| Validate Revisions | 2 days | Mon 3/12/01 | Tue 3/13/01 | 0%
| leiver report to Stemnet | 0 days | Tue 3/13/01 | Tue 3/13/01 | 0%
| implementation Cycle 3(Aug 2001-Jan 2002 | 34 days | Mon 8/6/01 | Thu 9/20/01 | 0%
| Update Evaluation tools | 10 days | Mon 8/6/01 | Fri 8/17/01 | 0%
| Distribute Evaluation Tools | 2 days | Mon 8/20/01 | Tue 8/21/01 | 0%
| Collect Data and Analyze Results | 10 days | Wed 8/22/01 | Tue 9/4/01 | 0%
| Review Evaluation Results with Team Leaders | 5 days | Wed 9/5/01 | Tue 9/11/01 | 0%
| Produce Draft Report | 5 days | Wed 9/12/01 | Tue 9/18/01 | 0%
| Validate Revisions and Dististribute Report | 2 days | Wed 9/19/01 | Thu 9/20/01 | 0%
| Validate Revisions | 2 days | Wed 9/19/01 | Thu 9/20/01 | 0%
| Deliver Report to International Conference | 0 days | Thu 9/20/01 | Thu 9/20/01 | 0%
| Deliver Report to Stemnet | 0 days | Thu 9/20/01 | Thu 9/20/01 | 0%
| Production of Final Evlauation Report (Feb-Mar 2002) | 21 days | Mon 2/4/02 | Mon 3/4/02 | 0%
| Synthesis of Overall Data | 4 days | Mon 2/4/02 | Thu 2/7/02 | 0%
| Consolidate with Team Leaders and On-site Teams | 4 days | Fri 2/8/02 | Wed 2/13/02 | 0%
| Modify Report | 5 days | Thu 2/14/02 | Wed 2/20/02 | 0%
| Produce Final Report | 5 days | Thu 2/21/02 | Wed 2/27/02 | 0%
| Submit Final Evaluation Report | 0 days | Mon 3/4/02 | Mon 3/4/02 | 0%
| Project Management | 399.25 days | Fri 9/15/00 | Thu 3/28/02 | 0%
| Project Leader | 152 days | Fri 9/15/00 | Mon 2/25/02 | 0%
| Finacial Managenment | 158 days | Fri 9/15/00 | Thu 3/28/02 | 0%
| Management of Team Leaders | 176 days | Fri 9/15/00 | Tue 12/18/01 | 0%
| Website Development | 46 days | Fri 9/15/00 | Thu 1/3/02 | 0%
| Non-School Days | 271 days | Fri 12/22/00 | Fri 1/4/02 | 0%
| Christmas 2001 | 11 days | Fri 12/22/00 | Fri 1/5/01 | 0%
| March Break 2001 | 10 days | Mon 3/19/01 | Fri 3/30/01 | 0%
| Summer 2001 | 50 days | Tue 6/26/01 | Mon 9/3/01 | 0%
| Cristmas 2002 | 10 days | Mon 12/24/01 | Fri 1/4/02 | 0%
| Project Ends | 0 days | Sun 3/31/02 | Sun 3/31/02 | 0%